## Agile Project Plan
AGILE PROJECT PLAN
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE | Comment From TL to Project Manager
| Product Release | Sir qahthani | 2022-09-02 | 2022-10-10 |  | 20% |  | SCOPE STATEMENT | Final Comment of Project Manager
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
| Sprint 1 |  | IT-Prog-E |  | 2020-09-03 | 2020-09-13 | 10 | Complete
| Feature 1 |  | IT-Prog-E |  | 2020-09-04 | 2020-09-14 | 10 | Complete
| Feature 2 |  | IT-Prog-E |  | 2020-09-05 | 2020-09-15 | 10 | Complete
| Feature 3 |  | IT-Prog-E |  | 2020-09-06 | 2020-09-16 | 10 | Overdue
| Sprint 2 |  | IT-Prog-B |  | 2020-09-16 | 2020-09-24 | 8 | In Progress
| Feature 4 |  | IT-Prog-B |  | 2020-09-16 | 2020-09-17 | 1 | In Progress
| Feature 5 |  | IT-Prog-B |  | 2020-09-17 | 2020-09-21 | 4 | Not Started
| Feature 6 |  | IT-Prog-B |  | 2020-09-22 | 2020-09-24 | 2 | Not Started
| Sprint 3 |  | IT-Prog-K |  | 2020-09-16 | 2020-09-24 | 8 | Not Started
| Feature 7 |  | IT-Prog-K |  | 2020-09-16 | 2020-09-17 | 1 | Not Started
| Feature 8 |  | IT-Prog-K |  | 2020-09-17 | 2020-09-21 | 4 | Not Started
| Feature 9 |  | IT-Prog-K |  | 2020-09-22 | 2020-09-24 | 2 | Not Started

## Agile Project Plan - BLANK
AGILE PROJECT PLAN
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE | Comment From TL to Project Manager
| Product Release | Sir qahthani | 2021-01-01 | 2021-01-31 |  | 0% |  | SCOPE STATEMENT | Final Comment of Project Manager
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
Sprint 1
Feature 1
Feature 2
Feature 3
Sprint 2
Feature 4
Feature 5
Feature 6
Sprint 3
Feature 7
Feature 8
Feature 9